## Sheet1
Agent | Output Summary | Error Cause | Blame Score
Alice (Product Manager) | Produced PRD mirroring the problem statement; noted large constraints and modular output; no algorithmic guidance. | Did not flag feasibility risks or require an $O(n)$/$O(n\log n)$ solution or acceptance tests for performance; left room for an exponential approach to slip through. | 2
Bob (Architect) | Authored system design choosing DP with memoization over bitmask state; class diagram (Game/DPState/FractionMod); sequence flow built around DP. | Chose an infeasible exponential-state DP (bitmask over up to 4×10⁵ balls → TLE/MLE); no complexity analysis; introduced unnecessary FractionMod and an extra DP state dimension (extra_turn) with no effect; ignored known linearity-of-expectation/comb combinatorics solution. | 5
Alex (Engineer) | Implemented game.py and main.py exactly per DP design; recursive bitmask DP, unused FractionMod, unused total_sum, redundant extra_turn in state; averaged over remaining balls. | Executed the wrong architecture: exponential complexity, deep recursion risk; wasteful state (trailing 0 in key, extra_turn unused); no performance guards/tests; solution fundamentally can’t run under constraints. | 4
QA Engineer | (No artifacts/logs) — no test plan or runs reported. | Failed to catch performance infeasibility (no large-n stress tests, no time/memory budget checks), allowing the DP approach to pass unchecked. | 3