## Sheet1
Agent | Output Summary | Error Cause | Blame Score
Alice (Product Manager) | Copied the original problem into the PRD; noted some ambiguity but provided no algorithmic guidance. | No direct technical error introduced; requirements were faithfully relayed. | 1
Bob (Architect) | Wrote the design stating: check sorted(a)==sorted(b); if n is even → always possible, if n is odd → parities must match. | Core theoretical mistake: the operation applies a transposition to both arrays each move, so the parity difference is invariant regardless of n. Claim “even n ⇒ any permutation” is false (e.g., n=2, a=[1,2], b=[2,1] is impossible). This wrong spec drives the downstream bug. | 5
Alex (Engineer) | Implemented the design verbatim in main.py: checked multiset equality; only enforced parity when n is odd. Implemented _get_parity using cycle update parity ^= (cycle_length + 1) % 2. | Two issues: (1) Propagated the architect’s wrong rule (no parity check for even n). (2) Parity computation is wrong — correct cycle contribution is (cycle_length - 1) % 2 (or parity = (n - #cycles) % 2), not (cycle_length + 1) % 2. Either bug alone can misjudge cases. | 4
QA Engineer | No tests or verification shown; no adversarial cases (e.g., n=2 counterexample) or property-based checks for parity invariants. | Process gap: lack of test coverage failed to catch the theoretical/spec error and the parity implementation bug before delivery. | 3