## Sheet1
Agent | Output Summary | Error Cause | Blame Score
Alice (Product Manager) | Drafted requirements and PRD for “beautiful array min operations” (array + k to make palindrome), saved as requirement.txt and PRD JSON/MD; renamed workspace to beautiful_array_min_operations. | Root misalignment: accepted and propagated the wrong problem statement (different Codeforces task) without validating against the actual user brief (string expression with +/×, fixed n-2 ops, merge digits, precedence). No clarification loop or sanity check. | 5
Bob (Architect) | Produced system design and class diagram for BeautifulArraySolver, InputHandler, Main; sequence diagrams and resources generated to implement the “beautiful array” logic. | Uncritical acceptance of incorrect PRD; designed APIs tied to n, k, arr I/O and palindrome ops, further cementing the wrong scope. Missed red flags like input shape mismatch vs intended n, s. | 3
Alex (Engineer) | Implemented main.py exactly per design: sorting pairs, checking diff % k, summing diff // k; I/O expects t, then n k and an integer array. | Built the wrong thing correctly: followed specs but failed to validate against problem statement or sample cases (should have noticed string input and operator insertion). Limited due diligence on I/O/spec sanity. | 2
QA Engineer | (No QA artifacts/logs present.) No test plan, no sample-case verification against the target problem (string with operators), no end-to-end validation. | Process gap: absence of QA allowed the requirement/design error to ship; would have caught I/O mismatch and functional mismatch with basic tests. | 4