## Sheet1
Agent | Output Summary | Error Cause | Blame Score
Alice (Product Manager) | Defined the project requirements and ensured that the high-level approach was aligned. Also provided clear task instructions. | Alice outlined the project's requirements and set the foundation. No specific coding or logic errors can be attributed here. | 1
Bob (Architect) | Drafted the system design, including the approach to be followed (greedy partitioning, prime factorization). Also confirmed the use of sympy for prime factorization and ensured the design was clear. | Bob provided a detailed design but did not address the exact partitioning algorithm strategy properly. A more specific definition of how the greedy algorithm should be applied could have helped avoid potential ambiguity. | 3
Alex (Engineer) | Wrote and reviewed the code (main.py) based on the design provided by Bob. Completed the integration with sympy and ensured the code was aligned with the product requirements. | Alex reviewed and wrote the code, but faced an issue with the wrong use of some mathematical constructs (e.g., incorrect combination of product factorizations for defining bad segments). Moreover, the initial code likely lacked clarity around how segments would be divided efficiently, which caused potential logic issues. | 4
QA Engineer | Performed checks for code correctness and integration validation. | QA Engineer did not appear to perform a robust validation or explicitly point out gaps in segment partitioning or the edge case handling in Alex's code. More testing on edge cases and validation could have caught potential issues before proceeding with deployment. | 3