## Sheet1
Agent | Output Summary | Error Cause | Blame Score
Alice (Product Manager) | Produced PRD and docs for monocarp_card_game; attempted PRD for attribute_check_game but PRD JSON failed to parse repeatedly. | Mermaid chart text embedded in JSON without escaping backslashes → JSONDecodeError (“Invalid \escape”). | 4
Bob (Architect) | Delivered architecture using frequency counts + sliding window over consecutive values; file layout and sequence diagrams provided. | No major design flaw; could have explicitly required shrinking the window on value gaps to guide implementation. | 2
Alex (Engineer) | Implemented CardGame.max_cards, GameManager, and CLI; code builds and runs. | Logical bug: only shrinks window when distinct count > k, but not when there’s a gap (values[right] - values[left] > right - left), so some optimal consecutive windows are missed; minor unused imports. | 5
QA Engineer | No visible test plan or execution; no unit/integration tests recorded. | Missing tests failed to catch PM’s JSON escaping issue and the sliding-window gap bug (e.g., cases like values [1,3]). | 3